## Q2 24
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
Region: XI |  |  |  | Calender Year: | 2024
Province: Davao de Oro |  |  |  | Quarter: | 2
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction/Upgrading of CVPH-Pantukan | Brgy. Kingking, Pantukan | 46400000 | 2019-10-24 | 2021-08-27 | 100% | 41617957.33 |  | Completed
Construction/Upgrading of CVPH-Pantukan - Phase II | Brgy. Kingking, Pantukan | 3600000 | 2021-03-13 | 2021-08-27 | 100% | 3233322.99 |  | Completed
Const. of IP House (Balai Mandaya-Mansaka) | Brgy. Pagsabangan, New Bataan | 20000000 | 2020-02-20 | 2023-10-28 | 97% | 15340803.49 | 21 | ADMIN. Materials only. Waiting for the delivery of materials to be used for landmark. Payment for the materials delivered on process.
Const. of IP House (Balai Tu Mandiba) | Brgy. Prosperidad, Montevista | 20000000 | 2020-02-20 | 2023-10-28 | 97% | 15000000 | 21
Const. of IP House (Balai na Linagsawan Tu Tribu Dibabawon) | Brgy. Awao, Monkayo | 20000000 | 2020-02-20 | 2023-10-28 | 97% | 15344654.49 | 21
Const. of Temporary Treatment & Monitoring Facility | Kingking, Pantukan | 10000000 | 2022-03-30 | 2023-05-09 | 100% | 8495113.26 |  | Completed
Road Upgrading/Improvement at Purok Side 4, Barangay Mangayon, Compostela | Purok Side 4, Mangayon, Compostela | 20000000 | 2021-08-31 | 2022-08-19 | 100% | 20000000 |  | Completed
Const. Of Water System at Barangay Maparat, Compostela | Maparat, Compostela | 20000000 | 2021-10-07 | 2022-12-31 | 100% | 10998534.4 |  | Completed
Road Upgrading/Improvement at Purok 1, Barangay Panansalan, Compostela | Purok 1, Panansalan, Compostela | 20000000 | 2021-09-07 | 2023-08-15 | 100% | 8825950.13 |  | Completed
Road Upgrading/Improvement Purok 4 to Purok 6, Barangay San Jose, Compostela | Purok 4-6, San Jose, Compostela | 20000000 | 2021-09-07 | 2022-08-02 | 100% | 20000000 |  | Completed
Road Upgrading/Improvement Purok 3, Barangay Tamia, Compostela | Purok 3, Tamia, Compostela | 20000000 | 2021-07-27 | 2022-08-20 | 100% | 20000000 |  | Completed
Upgrading of FMR at Barangay Datu Davao, Laak | Datu Davao, Laak | 12000000 | 2021-08-31 | 2022-06-09 | 100% | 4793467.5 |  | Completed
Const. of Water System at Barangay Datu Davao, Laak. | Datu Davao, Laak | 6000000 | 2021-11-29 | 2022-08-04 | 100% | 2546700.28 |  | Completed
Const. of Evacuation Center at Barangay Kapatagan, Laak | Kapatagan, Laak | 3000000 | 2021-10-07 | 2022-04-02 | 100% | 3000000 |  | Completed
Upgrading/Improvement of FMR at Barangay Kapatagan, Laak. | Kapatagan, Laak | 7000000 | 2021-08-31 | 2022-02-16 | 100% | 7000000 |  | Completed
Upgrading/Improvement of Candinuyan-Barigyan FMR, Golden Valley, Mabini | Golden Valley, Mabini | 10000000 | 2021-07-25 | 2022-01-18 | 100% | 10000000 |  | Completed
Upgrading/Improvement of Settler-Shanghai-Dasuran FMR, Mabini | Golden Valley, Mabini | 4000000 | 2021-07-25 | 2022-01-11 | 100% | 3999974.82 |  | Completed
Upgrading/Improvement of Bucana-Mambatang FMR | Anitapan, Mabini | 14000000 | 2021-07-25 | 2022-06-23 | 100% | 13999922.48 |  | Completed
Const. of Water System (Migum-Lower B), Barangay Cabuyuan | Cabuyuan, Mabini | 5000000 | 2021-10-07 | 2022-05-23 | 100% | 5000000 |  | Completed
Upgrading/Improvement of FMR at Barangay Gubatan, Maco | Gubatan, Maco | 9000000 | 2021-07-25 | 2022-06-25 | 100% | 9000000 |  | Completed
Const. of Level II Water Supply System at Barangay Gubatan, Maco | Gubatan, Maco | 5000000 | 2021-12-25 | 2022-06-21 | 100% | 5000000 |  | Completed
Sitio Electrification at Barangay Gubatan | Gubatan, Maco | 3000000 | 2022-02-15 | 2022-06-02 | 100% | 3000000 |  | Completed
Const. of School Building, Barangay Masara, Maco | Masara, Maco | 3000000 | 2021-12-06 | 2022-04-15 | 100% | 3000000 |  | Completed
Const. of Level II Water System, Barangay Masara | Masara, Maco | 3000000 | 2021-11-11 | 2022-06-24 | 100% | 0 |  | Completed
Const. of Level II Water System at Barangay Calabcab, Maco | Calabcab, Maco | 10000000 | 2021-11-11 | 2022-10-01 | 100% | 10000000 |  | Completed
Improvement of Health Center Calabcab, Maco | Calabcab, Maco | 1500000 | 2021-11-11 | 2022-02-02 | 100% | 1347606.49 |  | Completed
Sitio Electrification, Barangay Sangab, Maco | Sangab, Maco | 4000000 | 2021-11-25 | 2022-06-30 | 100% | 4000000 |  | Completed
Const. of Level II Water System, Brgy. Sangab, Maco | Sangab, Maco | 5000000 | 2021-11-25 | 2022-09-05 | 100% | 4999981.97 |  | Completed
Const. of Level II Water System, Brgy. New Asturias | New Asturias, Maco | 8000000 | 2021-11-15 | 2023-03-30 | 100% | 7997280.41 |  | Completed
Const. of School Building, Brgy. New Asturias | New Asturias, Maco | 2000000 | 2021-11-15 | 2022-05-10 | 100% | 2000000 |  | Completed
Road Concreting of Purok 4 and 5, Brgy. New Asturias, Maco | New Asturias, Maco | 5000000 | 2021-10-07 | 2022-02-21 | 100% | 5000000 |  | Completed
Const. of Health Station, Brgy. Magangit, Maco | Magangit, Maco | 2500000 | 2021-08-24 | 2021-12-20 | 100% | 2249947.69 |  | Completed
Upgrading of Water Supply System, Brgy. Bahi | Bahi, Maragusan | 3000000 | 2021-11-25 | 2022-06-19 | 100% | 2699977.91 |  | Completed
Upgrading of Water Supply System, Brgy. Mahayahay, Maragusan | Mahayahay, Maragusan | 2500000 | 2021-10-24 | 2022-01-22 | 100% | 2500000 |  | Completed
Conc. of Purok Rizal FMR, Brgy. Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-01-07 | 100% | 4399975.03 |  | Completed
Rehab. of Prk. Del Pilar-Prk. Jacinto FMR, Barangay Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-04-30 | 100% | 4499968.59 |  | Completed
Upgrading of Water Supply System, Brgy. Katipunan, Maragusan | Katipunan, Maragusan | 5000000 | 2021-11-25 | 2022-03-21 | 100% | 5000000 |  | Completed
Upgrading of Farm to Market Road at Purok 6 Brgy. Andili, Mawab | Andili, Mawab | 20000000 | 2021-09-30 | 2023-01-19 | 100% | 20000000 |  | Completed
Const. of Water Supply System, Brgy. Casoon | Casoon, Monkayo | 20000000 | 2021-12-02 | 2023-02-28 | 100% | 20000000 |  | Completed
Const. of Water Supply System, Brgy. San Jose, Monkayo | San Jose, Monkayo | 13000000 | 2021-10-07 | 2023-02-26 | 100% | 6498205.39 |  | Completed
Upgrading/Improvement of FMR at Brgy. San Jose, Monkayo | San Jose, Monkayo | 7000000 | 2021-09-30 | 2023-02-05 | 100% | 7000000 |  | Completed
Const. of Water Supply System, Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-10-07 | 2023-03-20 | 100% | 7997328.15 |  | Completed
Road Upgrading at Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-07-20 | 2022-08-04 | 100% | 10000000 |  | Completed
Const. of Water Supply System, Brgy. Upper Ulip, Monkayo | Upper Ulip, Monkayo | 10000000 | 2021-11-25 | 2023-01-18 | 100% | 8640163.38 |  | Completed
Rehab/Improvement of Water Supply System at Brgy Mt. Diwata, Monkayo | Mount Diwata, Monkayo | 10000000 | 2021-11-25 | 2023-02-10 | 100% | 8499953.13 |  | Completed
Upgrading/Improvement of FMR at Brgy. San Vicente, Montevista | San Vicente, Montevista | 20000000 | 2021-10-07 | 2022-09-13 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Magsaysay, Nabunturan | Magsaysay, Nabunturan | 20000000 | 2021-08-31 | 2022-09-25 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Andap, New Bataan | Andap, New Bataan | 20000000 | 2021-11-25 | 2023-12-06 | 100% | 19999935.86 |  | Completed
Upgrading/Improvement of FMR at Brgy. Bantacan, New Bataan | Bantacan, New Bataan | 20000000 | 2021-09-07 | 2023-05-21 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Cabinuangan, New Bataan | Cabinuangan, New Bataan | 20000000 | 2021-07-21 | 2023-03-28 | 100% | 20000000 |  | Completed
Electrification project at Barangay Manurigao, New Bataan | Manurigao, New Bataan | 20000000 | 2021-12-02 | 2023-10-15 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Pagsabangan, New Bataan | Pagsabangan, New Bataan | 20000000 | 2021-08-31 | 2023-03-15 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Kingking, Pantukan | Kingking, Pantukan | 20000000 | 2021-08-30 | 2022-09-14 | 100% | 20000000 |  | Completed
Improvement of "Ginintuang Paraiso" Public Park, Provincial Capitol Complex | Cabidianan, Nabunturan | 20000000 | 2023-05-10 | 2023-12-30 | 100% | 20000000 |  | Completed
Establishment of Feedmills | Pasian, Monkayo | 7500000 | 2019-11-28 | 2024-12-15 | 81.37% | 6103000 |  | Waiting for the completion of Phase 2
AFC Support Fund/Consultation Fund 2023 | Provincewide | 140000 | 2023-08-04 | 2024-08-04 |  | 0 |  | The payment for representantion expenses is on process under PO#24-02-0042.
Trichoderma Harzianum Project under HVCDP CY 2023 | Provincewide | 649250 | 2023-10-01 | 2024-11-01 | 33.37% | 216646 |  | On going
Procurement and Delivery of Trichoderma Packs (Support to Fusarium Wilt Mgt) | Provincewide | 5761600 | 2024-01-01 | 2024-12-31 |  | 0 |  | On going
Establishment of Multiplier Farm | Pasian, Monkayo | 5627255.16 | 2020-08-22 | 2022-12-31 | 98.31% | 5532353.24 |  | Completed
AFC Support Fund/Consultation Fund 2024 | Provincewide | 140000 | 2024-05-29 |  |  |  |  | Project design on process
Medical Assistance to Indigent Patient (MAIP) | Provincewide | 168812500 | 2023-03-15 | 2024-12-30 | 76.46% | 129082089.16 |  | On going
Implementation of Adoloscent Health and Development Program | Provincewide | 500000 | 2021-10-21 | 2022-10-21 | 74.48% | 372425 |  | Completed
Meals, Accomodation & Transportation Allowance (MAT) Benefits | Provincewide | 3843000 | 2022-05-18 | 2023-06-18 | 98.63% | 3790500 |  | Completed
Sustainment of Molecular Laboratory Operation | DDOPH-Montevista | 5000000 | 2003-12-04 | 2024-06-30 | 0% | 0 |  | PO awarded to ESCO Philippines Inc. (June 2024)
2022-Health Emergency Allowance (HEA)/OCA | Provincewide | 7788187.5 | 2023-11-13 | 2024-03-13 | 100% | 7788187.5 |  | Completed
Health Promotion Playbook (PA 6) | Provincewide | 500000 | 2023-08-30 | 2024-08-30 | 72% | 360000 |  | On going
Health Emergency Allowance (HEA)/OCA | Provincewide | 90354375 | 2024-05-29 | 2024-12-31 | 24.99% | 22579383.81 |  | On going
Gov't. Intership Program and Emergency Employment 2022 | Provincewide | 26751998 | 2022-11-03 | 2024-12-31 | 70.04% | 18736199.92 |  | On going
Share in PCSO-Lotto LGU Share | Provincewide | 392363.41 | 2023-07-01 | 2024-12-31 | 74.69% | 293060.77 |  | On going
Establishment of 30 SOW Level Swine Multiplier Farm (INSPIRE) Program | Provincewide | 10000000 | 2023-12-15 | 2024-12-15 |  | 0 |  | Delivered construction materials
PAFES Operation Fund for Co-Financing in DDO 2023-2025 | Provincewide | 875000 | 2023-07-27 | 2024-09-30 |  | 0 |  | The payment for representantion expenses is on process under PO#24-02-0042.
Assistance to Individual in Crisis Situation (AICS) 2024 | Provincewide | 20000000 | 2024-02-14 | 2024-12-31 |  | 13500000 |  | On going
Early Childhood Care and Development Council | Provincewide | 116000 | 2023-12-29 | 2024-12-29 |  | 0 |  | On going
Community Empowered through Science & Technology | Provincewide | 1500000 | 2023-12-10 | 2024-12-10 |  | 0 |  | On- going procurement
Livestock & Poultry Dev't. Program (Impv't. of Free-Ranged Chicken Production Facility) | Pasian, Monkayo | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | For Purchase Request
Brgy. Watershed Reforestation & Rehab.Project-Prk.5, Sitio Pinaupuan, Naga, Laak | Naga, Laak | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | On- going procurement
Brgy. Watershed Reforestation & Rehab. Project-Prk.7, Sitio Cadan, Kapitunan, Nabunturan | Katipunan, Nabunturan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | On- going procurement
Brgy. Watershed Reforestation & Rehab. Project-Prk.12, San Miguel, Compostela | San Miguel, Compostela | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | On- going procurement
Brgy. Watershed Reforestation & Rehab. Project-Prk.15, Bantacan, New Bataan | Bantacan, New Bataan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | On- going procurement
Brgy. Watershed Reforestation & Rehab. Project-Sitio Lanzones, Lahi, Maragusan | Lahi, Maragusan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | On- going procurement
0
| TOTAL | 999351529.07 |  |  |  | 782880570.57
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD.)ARIEL D. MANDAWE, CPA | (SGD.)EVA JEAN S. LICAYAN |  | (SGD.)ENGR. RODERICK M. DIGAMON |  |  | (SGD.)DOROTHY P. MONTEJO-GONZAGA
Provincial Accountant | Provincial Budget Officer |  | Provincial Engineer |  |  | Governor